DASHBOARD DESIGN & ACCEPTANCE SIGN-OFF

Dashboard 1 — Sign-off

Sales Data Warehouse — design baseline and acceptance for the first dashboard, produced on available SalesFlo secondary sales data.

| Client | Ana & Batla Industries |
| --- | --- |
| Project | Sales Data Warehouse |
| Document | TNX.DWH.AnaBatla.SO.01 |
| Version / Date | v1.0 — 29 August 2026 |
| Deliverable | Dashboard 1 — design pack and built dashboard (Milestone 3) |
| Governing documents | BRD TNX.DWH.AnaBatla.BRD.01 v1.0 · Project Plan TNX.DWH.AnaBatla.PP.01 v1.0 · Proposal TNX.DWH.AnaBatla.20260804.09 v09.0 |
| Prepared by | Tazeen Amir, Dashboard Design Lead — reviewed by Adnan Sajid, Project Manager / Data Engineer |
| Status | Issued for client sign-off |

# 1.  Purpose

This document closes the design of the first dashboard and records its acceptance. It states what was designed, what Ana & Batla asked to change at first revision, what is now built, and what remains open. Signature makes this design the baseline that the build is measured against.

The first dashboard was produced on the available SalesFlo secondary sales data, as set out in the Project Plan §5.1. Ana & Batla reviewed that design and returned one round of feedback. That feedback is incorporated in full and is recorded in §3 below. No further revisions are outstanding.

## 1.1  What signature confirms

- The filters, KPIs, visuals and business rules recorded in §3 are the approved design of Dashboard 1.

- The data displayed through the hosted application matches that approved design.

- Milestone 3 of the Project Plan — first dashboard delivered and accepted, revision rounds closed — is met on the date of signature.

- The three items in §4 remain open and are handled as recorded there. They do not hold up this sign-off.

- Any change requested after signature is handled through Change Control, per Project Plan §7.

# 2.  Revision history

Three revision rounds are included on the first dashboard under the Project Plan. One has been used.

| Round | Date | Outcome | Status |
| --- | --- | --- | --- |
| Rev 0 | Initial design | First dashboard design presented on available SalesFlo secondary sales data. | Superseded |
| Rev 1 | First revision | Client feedback on filters, KPIs and visuals received and incorporated in full. Recorded as the baseline in §3. | Approved — this document |
| Rev 2 / Rev 3 | Not used | Two of the three included rounds remain available on the first dashboard. | Available |

# 3.  Approved design baseline

The tables below record the design as approved at first revision. Items marked Removed were present in Rev 0 and are withdrawn at Ana & Batla's request; they are not defects and their removal does not reduce the agreed scope or fee.

## 3.1  Filters

| Filter | Treatment | Note |
| --- | --- | --- |
| Year | Retained | — |
| Month | Retained | Month-to-date default is the previous month (M-1). |
| Region | Added | Added at first revision. |
| Town | Retained | — |
| Channel Type | Retained | Channel names displayed in a hierarchy structure. |
| Category | Retained | — |
| Distributor | Retained | — |
| Date | Removed | Removed at first revision. |
| Business Unit | Removed | Removed at first revision. |
| Order Source | Removed | Removed at first revision. |

## 3.2  KPIs

| KPI | Treatment as approved |
| --- | --- |
| Primary Sales — Value & Volume | Retained. Volume expressed in Carton and Pieces. |
| Secondary Sales — Value & Volume | Added at first revision, shown alongside primary. Volume expressed in Carton and Pieces. |
| Total Store Count | Retained. |
| Productive Outlets (%) | Retained. |
| Segment-wise Sales | Added at first revision — General Trade, Export and Modern Trade. Primary data source only. |
| YTD | Calculated from 1 July, the fiscal year start. Comparison is current month against the same month of the previous year — for example August 2026 against August 2025. |
| Modern Trade | Currently tagged as a store type in SAP. Its MTD values are sourced from primary sales and must also be aggregated into secondary sales — where primary is PKR 1,000 and Modern Trade within it is PKR 300, that 300 is also added to secondary. Subject to §4, item OP-01. |
| Total Discount | Card removed at first revision. |
| Business Unit-wise Sales | Card removed at first revision. |

## 3.3  Visuals and sections

| Visual / Section | Treatment as approved |
| --- | --- |
| Channel Type Mix | Changed from vertical bar to horizontal bar at first revision. |
| Distributor Performance | Added — Target, Volume and Value (%), Total Outlets, Productive Outlets, and Drop Size (average sales value per outlet, plus overall distributor volume). |
| Region-wise Targets & Achievement | Added — primary and secondary. |
| Top Brands | Added — primary and secondary. |
| Net Sale by Category | Added — primary and secondary. |
| Classification-wise Productivity & Sales | Added. Pending the formula and secondary sales data — see §4, item OP-02. |
| SKU-level breakdown | Removed at first revision. |
| Distributor Sales Concentration | Removed at first revision. |
| Town Sales Concentration | Removed at first revision. |
| Business Unit Mix | Removed at first revision. |

## 3.4  Business rules applied

- Fiscal year begins 1 July. YTD figures are calculated from that date.

- The YTD comparison is the current month against the same month of the previous year.

- Month-to-date defaults to the previous month (M-1).

- Volume is expressed in Carton and in Pieces.

- Channel names are displayed in a hierarchy structure.

- Modern Trade is tagged as a store type in SAP; its MTD values are sourced from primary sales and are also aggregated into secondary sales, subject to OP-01.

- Segment-wise Sales is derived from the primary data source only.

- Metric definitions otherwise follow SAP standard Sales and Distribution practice, per BRD §4.3. A departure from that practice is agreed as a Change Request.

# 4.  Open items carried at sign-off

Three items were raised during review and remain with Ana & Batla. The design is approved and the dashboard is accepted with these carried as conditional items. Each is built to the treatment recorded in §3; a confirmation that agrees with that treatment requires no rework, and a confirmation that departs from it is assessed under Change Control.

| ID | Item | Owner | Treatment at sign-off |
| --- | --- | --- | --- |
| OP-01 | Modern Trade treatment in secondary sales aggregation | Irqam, Ana & Batla | Built to the rule in §3.2 — Modern Trade value sourced from primary and also added to secondary. Confirmation awaited. |
| OP-02 | Formula and secondary sales data for Classification-wise Productivity & Sales | Irqam, Ana & Batla | Section is laid out and reserved in the approved design. It is populated once the formula and the secondary data are supplied. |
| OP-03 | Meaning and filter treatment of the "SD" tag or exception in source data | Irqam, Ana & Batla | Records carrying the tag are currently included and not filtered out. Clarification awaited. |

How these are closed. Ana & Batla provides the three confirmations in writing by Friday 5 September 2026, five working days from issue. A confirmation that matches the treatment recorded above is applied as a correction at no cost and within the current schedule. A confirmation that departs from it, or one received after that date, is assessed by Technaptix and, where it changes a rule already built against, raised as a Change Request under Project Plan §7. Where no response is received, the treatment recorded above stands as the agreed rule.

# 5.  Acceptance

Acceptance of the first dashboard is the approval of its design and of the data displayed through the hosted application. Ana & Batla has five working days to accept, or to reject in writing citing the unmet criterion. Where no written response is received within five working days, the deliverable is deemed accepted, per BRD §6.1.

| ID | Acceptance criterion | Evidence |
| --- | --- | --- |
| AC-01 | The design of Dashboard 1 — filters, KPIs, visuals and business rules — is as recorded in §3 and is approved by Ana & Batla. | Design pack reviewed against §3; signature on this document. |
| AC-02 | First-revision feedback is incorporated in full, with the items marked Removed withdrawn. | Revision record in §2 and the treatment columns in §3. |
| AC-03 | The data displayed through the hosted application matches the approved design. | Review of the data displayed through the hosted application. |
| AC-04 | Open items OP-01 to OP-03 are recorded and their treatment at sign-off is stated. | Section 4 of this document. |

Deployment and handover. The dashboard is deployed and handed over to Ana & Batla at go-live. Acceptance under this document is the approval of the design and of the data displayed through the hosted application; it is not a handover event.

Milestone position. Signature of this document meets Milestone 3 of the Project Plan — first dashboard delivered and accepted with its revision rounds closed. Ana & Batla then provides the requirements for the remaining four dashboards, per BRD §4.5.

# 6.  Change control after sign-off

From the date of signature the design in §3 is the baseline. The following applies, per Project Plan §7.

- A change to the approved design of Dashboard 1 after acceptance is a Change Request.

- Two of the three included revision rounds remain available on this dashboard and are used for revisions raised before acceptance, not after it.

- Correction of an item that does not meet a criterion in §5 is not a change and is fixed at no cost.

- Cosmetic adjustment within the approved design that does not alter data, structure or visual count is not a change.

- A requirement needing data the warehouse does not hold is a Change Request.

- Approval of a Change Request requires signature from Irfan Khan for Ana & Batla and Haider Ali Mohsin for Technaptix. Work does not begin on an unsigned Change Request.

Approval & Signatures

By signing below, both parties confirm that the design recorded in §3 is the approved design baseline for Dashboard 1, that the dashboard as delivered is accepted against the criteria in §5, and that the open items in §4 are carried on the terms stated there.

| Signature Haider Ali Mohsin Chief Executive Officer, Technaptix Date | Signature Irfan Khan Head of Information Technology, Ana & Batla Industries Date |
| --- | --- |

Signature of this document constitutes acceptance of the first dashboard and closes its revision rounds. Any subsequent variation is managed through the Change Control process.